## Sheet1
Bug ID | Summary | Module | Expected Result | Actual Result | Severity | Priority | Status
BUG_01 | Locked user is unable to login | Login | User should be informed clearly that the account is locked and guided to contact support | Login is blocked with a generic error message | High | P1 | Open
BUG_02 | Login response is very slow | Login | User should be logged in within 2–3 seconds | Login takes unusually long time to respond | Medium | P2 | Open
BUG_03 | Product images and UI elements are not displayed correctly | Products Page | All images and UI elements should be displayed correctly | Images and layout are broken or incorrect | Medium | P2 | Open
BUG_04 | Error message is not user-friendly for empty login fields | Login | Clear validation message for both fields | Generic error message shown | Low | P3 | Open